## Rationale Register
CapEx Rationale Register (US GAAP / ASC 350-40)
Track rationale status for each capitalized project. One row per project.
Flowstate — flowstate.to
Project Name | Current Stage | Preliminary End Date | App Dev Start Date | App Dev End Date | Rationale Status | Estimated CapEx | Rationale Author | Last Updated | Notes
Payments Platform v2 | Application Development | 01/15/2026 | 01/18/2026 | 03/31/2026 | Complete | 252000 | J. Chen | 01/18/2026 | ARB sign-off triggered stage transition
Mobile App Redesign | Post-Implementation | 11/10/2025 | 11/15/2025 | 02/28/2026 | Complete | 189000 | S. Patel | 03/01/2026 | Closed out at go-live
Compliance Reporting | Post-Implementation | 12/20/2025 | 01/01/2026 | 02/15/2026 | Complete | 63000 | M. Torres | 02/16/2026 | Regulatory deadline
AI Recommendation Engine | Preliminary |  |  |  | Not Yet Required | 0 |  |  | Still evaluating build vs buy
[Your Project Name] | [5 empty] | 0
[Your Project Name] | [5 empty] | 0

## Rationale Template
CapEx Rationale — ASC 350-40 Stage Documentation
Complete one per capitalized project. Document stage transitions with evidence.
Flowstate — flowstate.to
Section | Guidance | Your Response | Evidence / Reference
Project Name | As it appears in your project management system | Payments Platform v2 | Jira: PAY-001
Software Type | Internal-use (ASC 350-40) or for sale (ASC 985-20)? | Internal-use
Business Context | Why does this project exist? How will the software be used? | Rebuild payments infrastructure to support 3 new payment methods and reduce cart abandonment by 8-12% | Business case BC-2026-003
PRELIMINARY STAGE
Activities Performed | What alternatives were evaluated? What feasibility work was done? | Evaluated 3 approaches: extend existing system, adopt third-party orchestrator, or full rebuild. PoC built for options 1 and 3 over 2 weeks. | PoC results in Confluence
Decision to Proceed | When and how was the go/no-go decision made? | Architecture review board approved full rebuild approach on 01/15/2026. VP Engineering confirmed budget allocation. | ARB minutes 01/15; budget email
Preliminary Stage End Date | Date the preliminary stage concluded | 01/15/2026 | ARB approval date
APPLICATION DEVELOPMENT STAGE
App Dev Start Date | Date capitalization begins — must be after preliminary stage ends | 01/18/2026 | First sprint of development phase
Activities Being Capitalized | What development work is in scope? | Detailed design, coding, unit testing, integration testing, data migration for new payment methods. | Sprint plans in Jira
Costs Being Capitalized | What cost categories are included? | Developer salaries (8 FTE), contractor costs (2 specialists), third-party Stripe/Adyen SDK licenses. | Resource plan; vendor contracts
Costs Excluded | What is NOT capitalized? | Training costs, general overhead, project management time, post-launch bug fixes. | Cost allocation policy
Expected Completion | When will the software be substantially complete? | 03/31/2026 | Project plan
Estimated Total CapEx | Planned capitalized investment | $252,000 | Based on 8 FTE × 2.5 months × $12.6K avg
POST-IMPLEMENTATION STAGE
Go-Live Date | Date software was substantially complete and in use | [To be completed at go-live]
Amortization Start Date | Same as or shortly after go-live | [To be completed]
Useful Life Estimate | Typically 3-5 years for internal-use software | 3 years | Per company accounting policy
Rationale Author | Who wrote this document | [Your name]
Date Authored | When this rationale was created | [Date]